## Campaigns
campaign_id | scope | frequency_required | opened_on | closed_on | status | reviewer | items_reviewed | items_revoked
ARC-2025-Q2 | Production privileged roles | Quarterly | 2025-04-07 | 2025-04-24 | Completed | cto@asteria.invalid | 31 | 2
ARC-2025-Q3 | Production privileged roles | Quarterly | 2025-07-07 | 2025-07-29 | Completed | cto@asteria.invalid | 33 | 1
ARC-2025-Q4 | Production privileged roles | Quarterly | 2025-12-01 | 2025-12-19 | Completed | cto@asteria.invalid | 34 | 3
ARC-2026-Q1 | Production privileged roles | Quarterly | 2026-03-02 |  | Abandoned | cto@asteria.invalid | 0 | 0
ARC-2026-Q2 | Production privileged roles | Quarterly |  |  | Not started | cto@asteria.invalid | 0 | 0

## Notes
campaign_id | note
ARC-2026-Q1 | Campaign opened during the platform migration and was not completed; reviewers were not reassigned.
ARC-2026-Q2 | Blocked pending the identity platform migration. Target restart date not agreed.
ARC-2025-Q4 | Last campaign completed. Three standing roles revoked.